## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  | 2024-11-14 | For YOLO model, Training system crashes with CPU | Sprint1 | Rohit Choudhary | Maintainability | GPU based | 2024-11-14 | Closed
2 |  | 2024-11-16 | Accuracy of Object Detection Model is Low | Sprint1 | Rohit Choudhary | Standards | Model Trained on Large Dataset | 2024-11-16 | Closed
3 |  | 2024-11-28 | Not able to figure out the best OCR | Sprint 2 | Rohit Choudhary | Standards | Used Image OCR | 2024-11-28 | Closed
4 |  | 2024-11-29 | Installation of ImageOCR | Sprint 2 | Rohit Choudhary | Maintainability | Checked with Python and Tensorflow different Versions | 2024-11-29 | Closed
5 |  | 2024-12-05 | Annotation of License Number Plates | Sprint 2 | Rohit Choudhary | Logical | Using Subtraction of the Co-ordinates | 2024-12-06 | Closed
6 |  | 2025-12-10 | Sort module not having class id | Sprint 3 | Rohit Choudhary | Logical | Used the earlier Yolo Model | 2025-12-10 | Closed
7 |  | 2025-12-20 | Missing Detections in some frames | Sprint 4 | Rohit Choudhary | User Interface | Interpolated the bounding boxes | 2025-12-21 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others